## BONIFACIO MM
cronograma fisico - financeiro convênio 0.305.395-22/09
| Discriminação dos serviços | Val. Obras/ | MÊS 1 | MÊ 2 | MÊS 3
Serviços
1.0 | SERVIÇOS PRELIMINARES | 14062.91 | 14062.91
2.0 | CARGA DE MATERIAL DE DEMOLIÇÃO E LIMPEZA | 1238.91 | 1238.91
3.0 | MOVIMENTAÇÃO DE TERRA | 6645.76 | 6645.76
4.0 | PAVIMENTAÇÃO | 202066.96 | 67355.6533 | 67355.6533 | 67355.6533
5.0 | SERVIÇOS COMPLEMENTARES
6.0 | PAISAGISMO | 5133.8 |  |  | 5133.8
[6 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| TOTAL | 229148.34 | 89303.2333 | 67355.6533 | 72489.4533
|  |  | 89303.2333 | 156658.8867 | 229148.34
Pirapora, 25 de outubro de 2013
Responsável Técnico
Moacir Moreira Filho
Arquiteto e Urbanista - CAU: A-12030-8
#VALUE!
#VALUE!